## Sheet1
KegID App Development status
Sr.No | Weeks | Functionality | Pages | Status | % Done | Remarks
1 | 1 | Architecture Setup for MVVM | Folder Structure and other Pattern MVVM | Done! | 70% | Still Showig Draft messages pending
2 |  | Login(With Service call mechanism
3 |  | will have to make it for across the app)
4 |  | Main Dash Board with swiping page ,
5 |  | Setting on topbar, showing draft message
6 |  | What is new, Support)
7 | 6 | Move functionality |  | Done! | 70%
8 | 2 | Fill |  | Done! | 70%
9 | 1 | Palletize |  | Done! | 70%
10 | 2 | Maintain |  | Done! | 70%
11 | 2 | Dash board detail views and listing of all summary |  | WIP | 60%
12 | 2 | Bluetooth printing and SQLite online offline mechanism |  | Pending | 0%
13 | 1 | Business login if anything I am not aware |  | Pending | 0%
14
15
16
17 | 17 | Total Weeks
What is New Discovered
|  |  |  | WIP | 20%
1 | 1 | Map functionality implementation for Partner locator
2 | 1 | Creating new Pages for e.g. Create new Batch, Add new Tags and so on there are several new item creation is happening while creating manifest, fill, palletize and maintain |  | WIP | 10%
3 | 1 | Printing template needs to setup
4 | 1 | Printer Setting needs to implement
5 | 1 | Sharing Option for e.g AirDrop in iOS like wise
6 | 1 | iOS app still not tested so not sure if any changes or UI will not work then needs to take care
7 | 2 | Whole App UI still needs to make it generic and theme base like font size, color, style,pop up and many more