## Sheet1
KegID App Development status
Time in Weeks
Sr.No | Weeks | Functionality | Pages | Status | % Done | Remarks
1 | 1 | Architecture Setup for MVVM | Folder Structure and other Pattern MVVM | Done! | 100%
2 |  | Login(With Service call mechanism
3 |  | will have to make it for across the app)
4 |  | Main Dash Board with swiping page ,
5 |  | Setting on topbar, showing draft message
6 |  | What is new, Support)
7 | 6 | Move functionality |  | Done! | 100%
8 | 2 | Fill |  | Done! | 100%
9 | 1 | Palletize |  | Done! | 100%
10 | 2 | Maintain |  | Done! | 100%
11 | 2 | Dash board detail views and listing of all summary |  | Done! | 100%
12 | 1 | Bluetooth printing mechanism |  | Pending | 0%
What is New Discovered
1 | 1 | Map functionality implementation for Partner locator |  | Done! | 100%
2 | 1 | Creating new Pages for e.g. Create new Batch, Add new Tags and so on there are several new item creation is happening while creating manifest, fill, palletize and maintain |  | Done! | 100%
3 | 1 | Printing template needs to setup
5 | 1 | Sharing Option for e.g AirDrop in iOS like wise |  | WIP | 50% | Still PDF Generating is missing
6 | 1 | iOS app still not tested so not sure if any changes or UI will not work then needs to take care |  | Done! | 100%
7 | 1 | Whole App UI still needs to make it generic and theme base like font size, color, style,pop up and many more |  | WIP | 80% | Some of the color code needs to address for e.g. Listview selected item BG color etc…
8 | 1 | KegHeld into Dashboad Parner manythings needs to address |  | Done! | 100%
9 | 1 | Resilient network services (needs to implement sercvice call mechanisam)
Fast response for our users (Cashing needs to implement)
10 | 1 | Work offline
Handling errors
11 | 1 | Code Optimization (code clean up, making generic function)
12 | 1 | Fill To Oder functionality
| Total Time: | 1.5 Months (Approx)
| Note : | If any tast may required RnD then timeline might be extend